## Publishing information
This publication was developed and published by the Energy Institute (EI). Copyright © 2022 by the Energy Institute, London. The Energy Institute is a professional membership body incorporated by Royal Charter 2003. Registered charity number 1097899, England Version 1.0, all rights reserved No part of this publication may be reproduced by any means, or transmitted or translated into a machine language without the written permission of the publisher. The information contained in this publication is provided for general information purposes only. Whilst the Energy Institute and the contributors have applied reasonable care in developing this publication, no representations or warranties, express or implied, are made by the Energy Institute or any of the contributors concerning the applicability, suitability, accuracy or completeness of the information contained herein and the Energy Institute and the contributors accept no responsibility whatsoever for the use of this information. Neither the Energy Institute nor any of the contributors shall be liable in any way for any liability, loss, cost or damage incurred as a result of the receipt or use of the information contained herein.

## Risk assessment matrix
UNDER TANK LINER RISK ASSESSMENT MATRIX
Consultant/Contractor: |  |  |  | Project: |  |  |  | Project ref: |  |  | Title: |  | Document number:
Likelihood (L) | Consequence (C) | [5 empty] | Likelihood (L) |  |  |  | Consequence (C) |  | Risk (R)
| Insignificant | Negligible | Moderate | Major | Catastrophic
Rare | 1 | 2 | 3 | 4 | 5 |  | Rare | May only occur in exceptional circumstances; ≤ 5% chance of occurring; task carried out once per project |  |  | Insignificant | No damage | Low (green) | Tolerable
Unlikely | 2 | 4 | 6 | 8 | 10 |  | Unlikely | Could occur at some time; >5% and ≤25% chance of occurring; task carried out 2 and ≤ 5 times per project |  |  | Minor | Minor superficial damage that is unlikely to affect integrity
Possible | 3 | 6 | 9 | 12 | 15 |  | Possible | Might occur at some time; >25% and ≤50% chance of occurring; task carried out > 5 and ≤ 15 times per project |  |  | Moderate | Minor superficial damage that is likely to affect integrity | Medium (amber) | Tolerable, monitor / manage
Likely | 4 | 8 | 12 | 16 | 20 |  | Likely | Will probably occur in most circumstances; >50% and ≤75% chance of occurring; task carried out > 15 and ≤ 25 times per project |  |  | Major | Moderate superficial damage that is likely to affect integrity | High (red) | Intolerable, must be mitigated
Almost certain | 5 | 10 | 15 | 20 | 25 |  | Almost certain | Can be expected to occur in most circumstances; >75% chance of occurring; task carried out > 25 times per project |  |  | Catastrophic | Serious permanent damage
Hazard |  |  | Initial risk rating |  |  | Measures taken to eliminate or reduce the hazard |  | Residual risk rating |  |  | Information communicated about the residual hazards | Date raised | Action by | Date actioned
|  |  | L | C | R |  |  | L | C | R
Tank construction
Liner puncture |  |  | Likely | Catastrophic | High | Careful planning and control of works Review of as-built drawings to understand base makeup so that methodology is appropriate Use of appropriate tools such as plastic shovels to minimise risk of damage to liner Careful removal of floor plates and use of machinery |  | Possible | Major | Medium | Toolbox talk carried out at job site, prior to works beginning. Hazards to liner communicated including: - Liner depth - Liner material - Consequences of puncture - Suitable tools, equipment and methods to be used | 2020-12-25 | SC | 2020-12-25
Liner tear |  |  | Likely | Catastrophic | High | Careful planning and control of works Construction traffic uses designated routes Low ground pressure equipment |  | Possible | Moderate | Medium | Toolbox talk carried out at job site, prior to works beginning. Hazards to liner communicated including: - Liner depth - Liner material - Consequences of puncture - Suitable tools, equipment and methods to be used | 2020-12-25 | SC | 2020-12-25
Liner disturbance |  |  | Likely | Catastrophic | High | Careful planning and control of works Review of as-built drawings to understand base makeup so that inspection methodology is appropriate Use of appropriate tools such as plastic shovels to minimise risk of damage to liner Care to be taken when working on tank shoulder |  | Possible | Moderate | Medium | Toolbox talk carried out at job site, prior to works beginning. Hazards to liner communicated including: - Liner depth - Liner material - Consequences of puncture - Suitable tools, equipment and methods to be used | 2020-12-25 | SC | 2020-12-25
Disturbance of base material |  |  | Likely | Catastrophic | High | Careful planning and control of works Review of as-built drawings to understand base makeup so that inspection methodology is appropriate Use of appropriate tools such as plastic shovels to minimise risk of damage to liner Care to be taken and mitigations if using ultra-high pressure (UHP) water or similar to cut plates Care to be taken when working on tank shoulder |  | Possible | Moderate | Medium | Tool box talk carried out at job site, prior to works beginning. Hazards to liner communicated including: - Liner depth - Liner material - Consequences of puncture - Suitable tools, equipment and methods to be used | 2020-12-25 | SC | 2020-12-25
Heat from welding |  |  | Likely | Catastrophic | High | Use of common base construction materials Use of approved weld techniques Works carried out by qualified welder |  | Possible | Moderate | Medium | Toolbox talk carried out at job site, prior to works beginning. Hazards to liner communicated including: - Liner depth - Liner material - Consequences of puncture - Suitable tools, equipment and methods to be used | 2020-12-25 | SC | 2020-12-25
Heat from oxyacetylene torch |  |  | Likely | Catastrophic | High | Careful planning and control of works Review of as-built drawings to understand base makeup so that risks are clearly understood Use cold cutting techniques instead Experienced and competent operator Toolbox talk prior to works commencing to reiterate risks and control measures |  | Possible | Moderate | Medium | Toolbox talk carried out at job site, prior to works beginning. Hazards to liner communicated including: - Liner depth - Liner material - Consequences of puncture - Suitable tools, equipment and methods to be used | 2020-12-25 | SC | 2020-12-25
Tank inspection using intrusive techniques
Heat from oxyacetylene torch |  |  | Likely | Insignificant | Low |  |  | Almost certain | Moderate | High
Liner puncture |  |  | Almost certain | Moderate | High |  |  | Almost certain | Moderate | High
Liner disturbance |  |  | Almost certain | Moderate | High |  |  | Almost certain | Moderate | High
Disturbance of base material |  |  | Almost certain | Moderate | High |  |  | Almost certain | Moderate | High
User-defined hazard |  |  | Unlikely | Moderate | Medium |  |  | Rare | Catastrophic | Medium
Floor replacement/ floor plate cutting
Liner puncture |  |  | Unlikely | Moderate | Medium |  |  | Almost certain | Moderate | High
Liner tear |  |  | Rare | Moderate | Low |  |  | Almost certain | Moderate | High
Liner disturbance |  |  | Rare | Moderate | Low |  |  | Almost certain | Moderate | High
Disturbance of base material |  |  | Rare | Moderate | Low |  |  | Almost certain | Moderate | High
Heat from welding |  |  | Rare | Moderate | Low |  |  | Almost certain | Catastrophic | High
Heat from oxyacetylene torch |  |  | Rare | Moderate | Low |  |  | Rare | Moderate | Low
User-defined hazard |  |  | Possible | Catastrophic | High |  |  | Unlikely | Moderate | Medium
Floor replacement/ floor plate welding
Heat from welding |  |  | Possible | Catastrophic | High |  |  | Almost certain | Moderate | High
User defined hazard |  |  | Unlikely | Insignificant | Low |  |  | Almost certain | Moderate | High
Floor refurbishment - shotblasting
Liner disturbance |  |  | Likely | Negligible | Medium |  |  | Almost certain | Moderate | High
Disturbance of base material |  |  | Possible | Insignificant | Low |  |  | Unlikely | Moderate | Medium
User-defined hazard |  |  | Almost certain | Moderate | High |  |  | Almost certain | Major | High
Base material removal
Liner puncture |  |  | Almost certain | Major | High |  |  | Almost certain | Insignificant | Medium
Liner tear |  |  | Almost certain | Major | High |  |  | Almost certain | Moderate | High
Liner disturbance |  |  | Almost certain | Moderate | High |  |  | Almost certain | Insignificant | Medium
Disturbance of base material |  |  | Almost certain | Moderate | High |  |  | Almost certain | Moderate | High
Settlement of base |  |  | Almost certain | Moderate | High |  |  | Almost certain | Major | High
User-defined hazard |  |  | Almost certain | Moderate | High |  |  | Almost certain | Insignificant | Medium
Liner repair - applies to liner as whole not local repair
Liner Puncture |  |  | Likely | Moderate | Medium |  |  | Almost certain | Moderate | High
Liner Tear |  |  | Unlikely | Negligible | Medium |  |  | Almost certain | Moderate | High
Liner Disturbance |  |  | Unlikely | Moderate | Medium |  |  | Almost certain | Moderate | High
Disturbance of base material |  |  | Unlikely | Moderate | Medium |  |  | Almost certain | Moderate | High
Settlement of base |  |  | Unlikely | Negligible | Medium |  |  | Unlikely | Moderate | Medium
User-defined hazard |  |  | Unlikely | Moderate | Medium |  |  | Almost certain | Moderate | High
Tank jacking
Liner puncture |  |  | Possible | Moderate | Medium |  |  | Almost certain | Moderate | High
Liner tear |  |  | Unlikely | Moderate | Medium |  |  | Almost certain | Moderate | High
Liner Disturbance |  |  | Unlikely | Moderate | Medium |  |  | Almost certain | Moderate | High
Disturbance of base material |  |  | Unlikely | Moderate | Medium |  |  | Almost certain | Moderate | High
Settlement of base |  |  | Unlikely | Moderate | Medium |  |  | Almost certain | Moderate | High
User-defined hazard |  |  | Unlikely | Moderate | Medium |  |  | Almost certain | Moderate | High
Roof support replacement
Liner puncture |  |  | Unlikely | Moderate | Medium |  |  | Possible | Moderate | Medium
Liner tear |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Liner disturbance |  |  | Unlikely | Major | Medium |  |  | Possible | Moderate | Medium
Disturbance of base material |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Settlement of base |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Heat from welding |  |  | Possible | Moderate | Medium |  |  | Unlikely | Moderate | Medium
User-defined hazard |  |  | Unlikely | Moderate | Medium |  |  | Unlikely | Moderate | Medium
Plant movements on base
Liner puncture |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Liner tear |  |  | Unlikely | Moderate | Medium |  |  | Possible | Moderate | Medium
Liner disturbance |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Disturbance of base material |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Settlement of base |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
User-defined hazard |  |  | Unlikely | Moderate | Medium |  |  | Unlikely | Moderate | Medium
Tank shoulder repairs
Liner puncture |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Liner tear |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Liner disturbance |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Disturbance of base material |  |  | Unlikely | Moderate | Medium |  |  | Possible | Moderate | Medium
Settlement of base |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
User-defined hazard |  |  | Unlikely | Moderate | Medium |  |  | Unlikely | Moderate | Medium
Vegetation Clearance
Liner puncture |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Liner Tear |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Liner disturbance |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Disturbance of base material |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
User-defined hazard |  |  | Unlikely | Moderate | Medium |  |  | Unlikely | Moderate | Medium
Burrowing animals
Liner puncture |  |  | Possible | Moderate | Medium |  |  | Unlikely | Moderate | Medium
Liner tear |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Liner disturbance |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Disturbance of base material |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
Settlement of base |  |  | Possible | Moderate | Medium |  |  | Possible | Moderate | Medium
User-defined hazard |  |  | Unlikely | Moderate | Medium |  |  | Unlikely | Moderate | Medium
Installation of double bottom in existing tank
Liner puncture |  |  | Unlikely | Moderate | Medium |  |  | Unlikely | Moderate | Medium
User-defined hazard |  |  | Unlikely | Moderate | Medium |  |  | Possible | Moderate | Medium
Retrofit of leak detection system by directional drilling
Liner puncture |  |  | Unlikely | Moderate | Medium |  |  | Possible | Negligible | Medium
Liner tear |  |  | Unlikely | Moderate | Medium |  |  | Possible | Moderate | Medium
Liner disturbance |  |  | Unlikely | Moderate | Medium |  |  | Possible | Moderate | Medium
Disturbance of base material |  |  | Unlikely | Moderate | Medium |  |  | Possible | Moderate | Medium
Settlement of base |  |  | Unlikely | Moderate | Medium |  |  | Possible | Moderate | Medium
User-defined hazard |  |  | Unlikely | Moderate | Medium |  |  | Possible | Moderate | Medium
Risk assessment revision history
Revision |  | Description | [9 empty] | Assessor | Checker | Date
[5 empty] | Catastrophic | 5
[5 empty] | Insignificant | 1
[5 empty] | Major | 4
[5 empty] | Moderate | 3
[5 empty] | Negligible | 2
[5 empty] | Almost Certain | 5
[5 empty] | Likely | 4
[5 empty] | Possible | 3
[5 empty] | Rare | 1
[5 empty] | Unlikely | 2